## Slide 1: Completing the Work: Monitor Project Scope, Schedule, and Budget
Dr. Emmanuel Ehimen Okoh

## Slide 2: LEARNING OBJECTIVES
By the end of this lesson, students should be able to:
Monitor project scope, schedule, and budget
Explain scope creep and gold plating
Understand why schedules and budgets are tracked
Resolve project variances using structured steps

## Slide 3: THINK-PAIR-SHARE (INTERACTIVE)
Question: Have you ever worked on a project that went off track?
What caused it?
Was it time, cost, or scope?
(Discuss with a partner for 2 minutes)

## Slide 4: THE TRIPLE CONSTRAINT
Scope = What to do
Schedule = When to do it
Budget = How much it costs
Activity: Which of these is most difficult to control? Why?

## Slide 5: MONITORING PROJECT PERFORMANCE
Monitoring involves:
Measuring performance
Comparing with plan
Identifying variances
Taking corrective action

## Slide 6: QUICK QUIZ (POLL)
Which of the following is NOT part of monitoring?
A. Measuring performance B. Ignoring problems C. Comparing with plan D. Taking action

## Slide 7: SCOPE CREEP
Definition: Uncontrolled expansion of scope without approval
Example: Adding new features without adjusting time or cost

## Slide 8: SCOPE CREEP
Causes:
Poor requirements definition
Lack of stakeholder alignment
Weak change control process

## Slide 9: ACTIVITY – IDENTIFY THE PROBLEM
Scenario: A client keeps requesting new features informally.
Question:
What is happening?
What should the project manager do?

## Slide 10: GOLD PLATING
Definition: Adding extra features not requested by the client.
Discussion: Why might this be harmful?
Key Insight:
Unlike scope creep (external pressure), gold plating is often internally driven by the team.

## Slide 11: GOLD PLATING
Effects:
Wasted resources
Increased risk of defects
Customer dissatisfaction (unexpected changes)
Maintenance complexity

## Slide 12: COMPARE (INTERACTIVE)
Fill the table:
Feature Scope Creep Gold Plating
Source
Approval
Impact

## Slide 13: Why Schedules Are Tracked
Tracking the schedule ensures that the project progresses as planned.
Reasons:
1. Detect Delays Early
Identifies slippage before it becomes critical
2. Maintain Deadlines
Ensures contractual obligations are met

## Slide 14: Why Schedules Are Tracked
3. Resource Optimization
Prevents over/under-utilization of team members
4. Supports Decision-Making
Enables corrective actions like:
  Crashing (adding resources)
  Fast tracking (parallel tasks)

## Slide 15: MINI EXERCISE
Project expected progress: 50% Actual progress: 30%
Question: Is the project ahead or behind schedule?

## Slide 16: Practical Example:
A construction project planned for 6 months:
After 2 months, only 20% completed instead of 33%
➡ Action:
Investigate delays
Add workers (crashing)
Adjust schedule

## Slide 17: Why Budgets Are Tracked
Budget tracking ensures financial control and project viability.
Reasons:
1. Prevent Cost Overruns
Keeps spending within approved limits
2. Ensure Profitability
Critical for business projects

## Slide 18: Why Budgets Are Tracked
3. Accountability
Tracks how funds are used
4. Forecasting
Predicts final project cost using tools like EVM

## Slide 19: Why Budgets Are Tracked
Example:
Budget = ₦1,000,000
Work completed = 40%
Actual spending = ₦600,000
➡ Indicates cost inefficiency → corrective action needed

## Slide 20: QUICK CALCULATION
Budget: ₦1,000,000 Spent: ₦700,000 Work done: 40%
Question: Is the project efficient?

## Slide 21: VARIANCE EXPLAINED
Variance = Difference between planned and actual
Types:
  Schedule variance
  Cost variance
  Scope variance

## Slide 22: SCENARIO ACTIVITY (GROUP WORK)
A project is:
  Behind schedule
  Over budget
  Scope is increasing
Task: Identify the problems and suggest solutions

## Slide 23: STEPS TO RESOLVE VARIANCES
Identify the problem
Analyze the cause
Evaluate impact
Develop solutions
Implement change control

## Slide 24: Resolving Variances (Scenario-Based Approach)
Step-by-Step Framework
Step 1: Identify the Variance
Scope variance
Schedule variance
Cost variance

## Slide 25: Resolving Variances (Scenario-Based Approach)
Step 2: Analyze Root Cause
Poor estimation?
Resource shortage?
Scope changes?

## Slide 26: Resolving Variances (Scenario-Based Approach)
Step 3: Evaluate Impact
On timeline
On cost
On quality

## Slide 27: Resolving Variances (Scenario-Based Approach)
Step 4: Develop Corrective Actions
Scope control
Schedule adjustment
Budget reallocation

## Slide 28: Resolving Variances (Scenario-Based Approach)
Step 5: Implement Change Control
Submit change request
Get approval
Update project documents

## Slide 29: Resolving Variances (Scenario-Based Approach)
Scenario Example
A project to build an e-learning platform:
Planned duration: 4 months
After 2 months: only 25% complete
Budget nearly exhausted

## Slide 30: Resolution Steps:
Stop unauthorized scope additions
Reassess remaining work
Prioritize critical features
Apply schedule compression
  Fast tracking
  Crashing
5. Reforecast budget
6. Communicate with stakeholders
7. Submit formal change request if needed

## Slide 31: Another Scenario (Scope Issue)
Problem:
Client keeps requesting small changes informally.

## Slide 32: Another Scenario (Scope Issue)
Solution:
Enforce Integrated Change Control
Document all requests
Assess impact before approval
Reject or defer non-critical changes

## Slide 33: ROLE PLAY (INTERACTIVE)
Roles:
  Project Manager
  Client
  Team Member
Scenario: Client requests extra features late in project
Act out how to handle it professionally

## Slide 34: CLASS DISCUSSION
What happens if:
  Scope is controlled, but budget is not?
  Budget is controlled, but schedule is not?

## Slide 35: Summary
Schedule tracking ensures timely delivery.
Budget tracking ensures financial control.
Variances must be:
  Identified
  Analyzed
  Controlled through structured processes

## Slide 36: EXIT TICKET
Write briefly:
One thing you learned today
One question you still have

## Slide 37: .
QUESTIONS